## Slide 1: Update on the Relocation of NSF Headquarters
Business and Operations Advisory Committee
November 29, 2016
Dr. Joanne Tornow
Brian MacDonald

## Slide 2: Project Overview
NSF relocating to Alexandria in 2017
  Moving 2,250 people
  Moving into brand new building
  NSF located under one roof
  Relocate between August and October 2017
  Rent reduced by $6 million per year

## Slide 3: Helping NSF achieve its mission
New Panel Conference Center
  37 conference rooms accommodating 1,200 people
  Modern AV capabilities
  Visitor Center, Business Lounge, Pre-Function Area
Work from anywhere in the building
  Robust Wi-Fi, print to any printer, VoIP system
Improves NSF’s compliance with various federal mandates, statutes, and Executive Orders.

## Slide 4: Helping NSF achieve its mission
NSF controls building security
  Dedicated NSF parking garage w/controlled access
  NSF-only vs. public space
Improved building design
  Smart elevator system reduces wait times by 60%
  Improved energy efficiency (LEED Silver certification)
  Employee amenities (full service cafeteria, fitness center)

## Slide 5: Project Timeline
Chart: 
| Prospectus Approved | Lease Award | Construction Begins | Final Design Decision | Redesign Begins | Interior Construction Begins | Construction Ends | Relocation Complete
 | 0 | -5 | 7 | -7 | 10 | 8 | -5 | -15 | 7
 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WE ARE HERE

## Slide 6: Schedule and Budget Update
Project is on schedule
  Data Center complete & commissioned
  5th floor construction 95% complete
  Employee workspace and furniture selections complete
  Absorbing schedule slippage
  Sequence of moves established
Project costs are trending slightly below budget
  Upcoming high value procurements
  Sufficient contingency remaining

## Slide 7: Managing Risks
Integrated Project Schedule
  Tracking critical path activities
Business operations readiness
  Collaborating across OIRM
Partnering with BFA

## Slide 8: Building Skyline

## Slide 9: Building Exterior

## Slide 10: 5th Floor

## Slide 11: Change Management/Communications
FY16 FEVS: 74% satisfied with communications about the move
Integrated communications team
Connecting to the new building:
  Relocation resources on Inside NSF
  Workspace selection
  Monthly bus tours to vicinity
  Directorate branding
  Video tour
  Plan to initiate building tours in late winter 2017

## Slide 12: Directorate Branding

## Slide 13: Directorate Branding

## Slide 14: Video Tour

## Slide 15: What happens after we get there?
What do we need to start doing now to prepare for post-move?
  Avoiding let-down for staff responsible for all aspects of relocation.
  Best practices for agency staff to adjust to new surroundings/new processes.